Interlake Sailing Class Association

National Race Committee Manual

Revised: 16-Jul-05

###### Table of Contents

##### Section	Page

1	INTRODUCTION	3

1.1	Preface	3

1.2	Organization	4

1.3	ISCA Executive Committee	4

1.4	National Race Committee	5

1.5	Local Committee	6

1.6	Sample Timetable	7

2	NATIONAL RACE COMMITTEE	8

3	LOCAL COMMITTEE	10

3.1	Introduction	10

3.2	Finance	10

3.2.1	Entry Fee	10

3.2.2	Other Fees and Expenses	12

3.2.3	Financial Summary	12

3.3	Reception	12

3.4	Housing	14

3.5	Lunches and Refreshment	14

3.6	Social	15

3.7	Mementos	15

3.8	Banquet	15

3.9	Launching and Mooring	16

3.10	Clean Up	16

3.11	Appeal	16

3.12	Liability Insurance	16

3.13	Junior Nationals and Women’s Championship	16

3.14	Publicity	17

4	MEASUREMENT	18

4.1	Introduction	18

4.2	Sail Measurement	18

4.3	Boat Measurement	19

4.4	Bow Numbers	20

4.5	Boat Weighing	20

4.6	Summary	21

5	RACE MANAGEMENT AND JUDGING	21

5.1	Introduction	21

5.2	Organization	21

5.3	Race Officers	22

5.4	Judges	22

5.5	Protests	23

5.6	Requests for Redress	23

5.7	Selection of Race Officers and Judges	24

5.8	Summary	24

6	NOTICE OF RACE	25

7	ENTRY FORM	27

8	SAILING INSTRUCTIONS	29

9	NRC QUESTIONAIRE	33

10	REVISION LOG	34

# INTRODUCTION

## Preface

The National Championship Series (NCS) is one of the cornerstones upon which the Interlake Sailing Class Association has been built and the most exposed area in which the membership and the general public judges the expertise and vitality of the ISCA.  The NCS selects a champion who symbolizes the Association and represents the ISCA at the US SAILING Championship of Champions Regatta.  In addition, this event publicizes and promotes the Interlake among sailors everywhere, but particularly at the site of the regatta itself.  Through the years, the reputation of the Association and the NCS has been built on intense, fair competition; warm camaraderie; and family racing.  To maintain this record of excellence, the following objectives must be met: 
1.	Good facilities, carefully managed.
2.	Championship quality race courses.
3.	Championship quality race management and judging.
4.	Adequate housing and camping.
5.	Social activities that appeal to all.
6.	The finest hospitality.

This manual serves several purposes.  First, it is a checklist to insure that no important item is overlooked.  Secondly, it sets forth the authority and responsibilities of the various groups who must work together smoothly in order to achieve the objectives listed above.  Lastly, it preserves the experiences and lessons learned by previous National Race Committees to avoid repetition of the errors of years past and to aid in the improvement of the event.

Several principles guide the Association in the selection of sites for the National Championship Series:

- The Association wishes to alternate, if possible, between Great Lakes and inland sites.

- The traditional date for the event is the second week of August after ILYA Bay Week. Consideration must also be given to school districts in Ohio, Indiana, and elsewhere that may start school in the second week of August.  An example is shown below:

|  | Sun | Mon | Tues | Wed | Thur | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- | --- |
| July ILYA Junior Bay Week | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 |
| August ILYA Bay Week | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
|  | 10 | 11 | 12 | 13 | 14 School Starts? | 15 School Starts? | 16 |

- The location should help boost local fleets in existence or help promote the establishment of new fleets.

The site should be capable of presenting a national championship regatta in terms of personnel and facilities.

Bids to host the National Championship Series must be submitted by mid-October of the second year preceding the event so that all bids can be evaluated and the best site chosen by November of that year.

## Organization

The overall organization of the National Championship Series is shown on the chart above.  The responsibilities of the various units are described below.

## ISCA Executive Committee

The Executive Committee of the ISCA appoints the five members of the National Race Committee plus alternates.  The alternates should be appointed in order so that in case of one or more vacancies on the NRC, the order of succession is clear.  The makeup of the NRC should include top competitors, sailors who have demonstrated some organizational ability but who may be novices, sailors from the Great Lakes, and sailors from inland waters.  One member, usually the Chairman of the Local Committee, must be from the host club.    The Executive Committee accepts the proposal to host the NCS from the host club but after the bid is accepted, the Association's contact with the Local Committee is through the National Race Committee.  By limiting official contact in this manner, confusion can be minimized.

The Executive Committee also appoints a Measurement Committee, which is responsible for the weighing and measuring at the National Championship Series.

The ISCA Secretary-Treasurer provides the following materials to the NRC for distribution as necessary to the NRC members or members of the Local Committee:
List of Entrants
Protest Forms.

Pre-registrations can now be sent to the host club, since the 14-day membership requirement was removed in 2004. The Secretary-Treasurer will provide a list of members to compare against the entry list. Persons who are not members must join the ISCA before the close of registration at the regatta site.  All of the dues received go to the Association.

The Chief Measurer is responsible for overseeing, either personally or through members of the Measurement Committee, the weighing and measuring of the entered yachts.  The Chief Measurer will generate both Hull Measurement and Sail Measurement Forms for distribution to the Measurers.  The Measurement Committee supplies the following materials to the Measurers:
A member to oversee the measurement process
Hull Measurement Form blank form
Sail Measurement Form blank form
Scales. Calibration weights are not necessary as long as the electronic scales are used.
Measurement templates for measuring hulls
Sail measurement templates (requires approximately 30'x30' area)
Sail measurement stamp and stamp pad.

## National Race Committee

The National Race Committee acts as the liaison between the ISCA and the Local Committee.  In particular, the NRC approves the selection of the Protest Committee and the Principle Race Officer (PRO) recruited by the Local Committee and provides certain materials to the Local Committee (see Section 2 National Race Committee).    The NRC shall continually review the progress, arrangements, and plans of the Local Committee to be absolutely certain that everything is in readiness.  The individual members and Committee as a whole are encouraged to be inquisitive and thorough in this regard.  They must make suggestions whenever appropriate and, in extreme cases, be prepared to step in and pick up the pieces.

On the positive side, the NRC should provide early, continuous, and detailed direction to the Local Committee so that they know exactly what is expected of them.  Initially, this is provided through this manual and the Local Committee Chairman's membership on the NRC.

Various members of the National Race Committee must obtain the following items for use by themselves or the Local Committee:
Notice of Race (see Section 6)
Sailing Instructions (see Section 8)
Excel Scoring Spreadsheet or other appropriate software, a computer to run it, and a printer to print out the results for posting.
Trophies:
Perpetual: Championship, Challenger, Championship Crew, and Best Fleet Participation.
Championship: Skipper and crew for first through tenth place, and Best First NCS Outside of the Top Ten.
Challenger: Skipper and crew for first through third place.
Final Registration Forms
General Information Sheets.
Fleet Ribbons
Copies of this manual for the Principle Race Officer and Protest Committee
A copy of the ISCA Constitution, Bylaws, and Specifications for the Protest Committee’s use.

## Local Committee

The Local Committee's job is perhaps hardest of all.  They must plan well in advance for a week's frenzied activity and be prepared to deal with the vagaries of weather, luck, and a group of outsiders called the ISCA National Race Committee.  They must recruit volunteers to provide several services, which often means talking people into giving up hard earned vacation time.  A large committee with responsibility well-distributed serves to divide the responsibility into several easily handled tasks so that most of the Local Committee members can also compete in the event without insurmountable strain.

The Local Committee must recruit a Principle Race Officer and Judges who are acceptable to the NRC.  After acceptance, the Principle Race Officer's direction comes from the NRC rather from the Local Committee.  Similarly, volunteers to staff the weighing and measuring operation must be recruited, but this operation will be under the control of the ISCA Measurement Committee once measurement begins.

The duties of the Subcommittees are detailed below but the organization of the Local Committee (aside from the Judges, Race Officers, and Measurers) is entirely at the discretion of the Local Committee itself.

The Local Committee is responsible for obtaining the following items (if difficulty is encountered, the NRC may assist):

- Race Officers (meals and lodging provided)

- Judges (meals and lodging provided)

- Race Officer equipment including:

| Race committee boats | Rescue Boats | Gas and other supplies | Race officer refreshments |
| --- | --- | --- | --- |
| Hailers | Cannon and shells | Signals and horns | Signal flags or shapes |
| Radios | Course marks, including stake boats, if required. |  |  |

- Cooperation with the Coast Guard or local Marine Patrol

- Marine Event Permit (where required)

- Meeting rooms for protest hearings Competitors Meetings, and the ISCA Annual Meeting

- A place for the reception and final registration desk

- The awards banquet

- Lunches at a reasonable charge

- Room to measure sails (at least 30' by 30')

- Suitable equipment to weigh yachts (a manual or power hoist with 110 VAC power nearby)

- Space to store boat trailers

- Personnel to help launch yachts, weigh yachts, measure sails, spars, and hulls, man the stake, service, and rescue boats, and staff the reception and final registration desks.

- Liability insurance.  The US SAILING has recently extended their regatta liability program so that member clubs and organizations may avail themselves of this coverage.  Alternately, the event may be covered by the Host Club's policy (by rider if necessary).

## Sample Timetable

| Date | Event |
| --- | --- |
| 2nd Year Previous |  |
| Mid-October | Host Club: Presents an offer in writing to the ISCA Executive Committee with location, dates, and the name of the Local Chair. The deadline is the Fall Meeting of the Association. |
| Mid-November | Executive Committee: Accepts the offer by a formal resolution at its fall meeting. |
| Previous Year |  |
| August | Vice President: At the ISCA Annual Meeting, a Vice-President is elected and becomes the Chair of the National Race Committee (NRC). |
| November | Local Committee: Selects a Principal Race Officer (PRO) and Judges. Executive Committee: Approves the NRC Manual and has copies printed. At the Executive Committee meeting, NRC members are appointed. The Local Chairman is one of these appointees. NRC Chair: sends a letter to the members notifying them of their appointment. ISCA Secretary Treasurer: sends a copy of the NRC Manual to each member. |
| Year of the Event |  |
| January | NRC Chair: Mails out the questionnaires (Section 9) along with the notice of the first NRC meeting |
| 2nd or 3rd weekend in January | Executive Committee: Meets. |
| February | National Race Committee (NRC): Meets. Approves PRO and Judges. PRO and Chief Judge: Attend the meeting and review separation of responsibilities in the NRC Manual. NRC Chair: Distributes responsibilities among the NRC members and distributes the draft notice of race (Section 6) and sailing instructions (Section 8). Possible changes are discussed with the Committee, the PRO, and the Chief Judge. |
| March | Executive Committee: Meets. |

| Date | Event |
| --- | --- |
| First Weekend of May | Chiefs Regatta, Columbus, OH NRC: Meets and accepts or modifies a fee schedule proposed by the Local Chair. The Sailing Instructions are reviewed and final changes made. Executive Committee: Meets and approves the fee schedule and distribution. The Local Committee can immediately draw the guaranteed amount from the Secretary-Treasurer. The ISCA Spring Meeting is held. |
| June | NRC Members: Finalize, print, and send copies of the Sailing Instructions to the Local Committee. NRC Chair: Verifies the status of preparations by NRC members (trophies, scorecards, etc.) and reviews plans for measurement with the ISCA Chief Measurer. |
| 10 Days before the 1st Race (Late July) | Secretary-Treasurer: Sends a complete list of ISCA members and a check to the Local Committee. Marketing Committee Chair: Prints envelopes from the list of publications in the US SAILING Regatta Reporting Service. |
| Day before the 1st Race (August) 1700 hrs | NRC: Meets and discusses final preparation and makes plans for the Competitors Meeting All Race Officers and all Judges should attend this meeting |
| 1800 hrs | Executive Committee: Meets. |
| 2000 hrs | Competitors Meeting |
|  | -- After the Event -- |
| Week Following | Publicity Chair: Completes and mails the US SAILING Regatta Reporting Service forms to magazines and other publications. |
| August 31 | Publicity Chair: Submits article(s) to the Intercom Editor |
| August-September | Local Committee: Prepares a financial summary and sends to the ISCA Secretary-Treasurer along with comments or suggestions to improve the event or the NRC Manual. |

# NATIONAL RACE COMMITTEE

The duties and responsibilities of the NRC have been detailed in Section 1.  This section will provide some guidance and detail in the accomplishment of these tasks.  The first order of business is to become acquainted with the personnel and overall capabilities of the Local Committee.  This is especially important if the host club has not before been the site of the National Championship Series.  Will the Local Committee need little or no assistance?  How best to provide the assistance required without interfering unduly with the Local Committee's autonomy?  Can the members of the Local Committee offer advice and suggestions to the NRC that will improve the event?  Each year the NRC must discern the answers to these and other important questions.  Be diplomatic here.  Although the NRC has overall authority, the various members of the Local Committee are volunteers and, as such, generally have a low tolerance level for perceived abuse and interference.  It is essential that the NRC remain helpful to the Local Committee throughout the planning and execution of the National Championship Series.

The Chairman of the NRC should divide up the responsibility of supplying the various items to the Local Committee.  As an aide, a NRC member questionnaire (Section 9) will seek to elicit volunteers and identify people with talents or connections in specific areas.  An important area is designating a scoring subcommittee to handle the tasks of transposing the scores from the recording sheets used by the Race Officers to the Lotus spreadsheet and permanent record sheets.  The Chairman should NOT be on this subcommittee as since the purpose of establishing this group is to free the Chairman from this specific worry.  Particular care should also be attached to the task of assembling the Sailing Instructions for review by the NRC, Judges, and Race Officers.  This should be assigned to someone with a firm grasp of the ISAF Racing Rules of Sailing (RRS) and the experience of past National Championship Series.  Undoubtedly, the Sailing Instructions can always stand improvement or modification so fit local circumstances, but modifications should not be considered lightly.

In regard to the selection of Judges and Principal Race Officer (See Section 5), it is preferred to have one or more US SAILING Certified Judges on the Judges Committee.  The US SAILING Directory provides the names and addresses of judges within the area.  This idea should be specifically recommended to the Local Committee before they have made a search for a Principal Race Officer and Judges.

Usually, the NRC meets before the Competitors Meeting to finalize any plans and to assure that all is in readiness.  This meeting should include the Principal Race Officer and the complete Judges Committee.  A final review of the Sailing Instructions should be conducted to insure that the Principal Race Officer, Judges, and the National Race Committee are absolutely unanimous in their opinions on the various sections of the Sailing Instructions.  At this time, if not earlier, the Race Recording Sheets and list of entrants should be given to the Principal Race Officer so that race finishes may be properly recorded.

At the Competitors Meeting, the Chairman of the National Race Committee should make some introductory remarks and introduce the Judges and Race Officers.  Each introduction should include a brief description of the person's qualifications and background.  A discussion of the Sailing Instructions should NOT be necessary and should be discouraged by the NRC Chairman.  The Principal Race Officer should field most of the questions.  The answers given should be in accordance with the NRC Chairman's understanding and he should hasten (diplomatically, of course) to correct any inaccuracies in the Principal Race Officer's responses.  Ironing out differences can be left until later in private, but clear-cut, unanimous direction should be given to the assembled racers.  REMEMBER:  Any change to the sailing instructions cannot be made verbally and must be posted as an official notice!

After each day's racing, members of the Scoring Subcommittee should take the Race Recording Sheets and Protest Forms (if any) and transfer the results onto the spreadsheet or scoring program and make a printout.  A minimum of two persons should review the output to insure against errors.

The NRC should conduct a quick Competitors Meeting after the fleet has been split into Championship and Challenger Divisions so that all members of the Challenger Division are explicitly aware of the timing of their start relative to the Championship Division start.    The standings should be posted each evening so that the sailors may examine them for possible errors and ponder the portent of the assembled scores.  This last practice doesn't seem to do much good, but it seems popular nonetheless.

The results for the entire event should be displayed at the banquet, but only if duplicate scores are safely recorded elsewhere.

A copy of the results, including elimination series, should be sent to both the Intercom Editor and the Past President (so that Traveler’s Trophy points may be awarded).

# LOCAL COMMITTEE

## Introduction

The Local Committee's duties are the hardest and longest.  The purpose of this Section is to provide guidance and a checklist to aid the Local Committee in the discharge of its functions.  Excluded from this Section are the Subcommittees of Measurers (Section 4), and Race Officers and Judges (Section 5).

## Finance

One person can usually handle the duties of the Finance Subcommittee.  Basically the job consists of constructing a budget, setting or negotiating various fees, receiving funds, paying bills, and preparing a brief statement to summarize the financial aspects of the regatta.  This Chairman should have either a separate bank account for the fleet funds or a sufficiently detailed record system.

The Finance Subcommittee Chairman should review this Section and Section 5 Race Management and Judging and estimate amounts for the various expenses, particularly the complimentary services provided to the Race Managers and Judges.  The minimum number of yachts likely to attend should be estimated.  Beverages, lunches, land the banquet should be priced to be self-sufficient.

When this has been done, an entry fee may be negotiated with the ISCA through the NRC Chairman, which will recover these expenses through the minimum number of registrants expected.  The Chairman should preserve these records carefully to assist in preparation of the final statement.

### Entry Fee

To estimate the number of entrants, the number of boats likely to attend from other clubs (“visitors”) should be added to the number expected from the host club.  To aid in planning, here are the number of total and visiting boats for the period 1973-2002.  “Visitors” are people who aren’t likely to sleep in their own beds, e.g. Hoover YC visitors exclude Leatherlips YC entrants and North Cape YC visitors excludes all Toledo boats:

| Year | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Host Club | HPYC | ISC | NCYC | HYC | SSC | PIBYC | ILYC | GTYC | PCYC | PYC | NCYC |
| Total | 27 | 31 | 34 | 36 | 59 | 26 | 49 | 43 | 37 | 34 | 41 |
| Visitors | 17 | 18 | 24 | 21 | 33 | 26 | 38 | 35 | 31 | 21 | 28 |
| Entry Fee | $50 | $50 | ? | $50 | $60 | $35 | $65 | $75 | $75 | $75 | $75 |

Each entry fee is divided into two parts; one portion to the ISCA and one portion to the host fleet.  Any late fees as well as all entry fees for the Junior and Women's Championships go entirely to the host club.  A summary of the entry fees over the past several years appears below.

Entry Fee Distribution
Interlake National Championship Series

| Year Site | 1977 Put-In-Bay | 1978 Glen Lake | 1979 Sandusky | 1980 Indian Lake | 2003 Portage Lake |
| --- | --- | --- | --- | --- | --- |
| Entry Fee ($) Late Fee ($) No. of Entrants: | 24.00 11.00 57 | 27.00 10.00 62 | 25.00 10.00 51 | 25.00 10.00 42 | 75.00 20.00 37 |
| 1-30 Entrants Host Club ISCA Subtotal-Host Club | 10.00 14.00 300.00 | n/a | n/a | n/a | n/a |
| 31+ Entrants Host Club ISCA Subtotal-Host Club | 14.00 10.00 378.00 | n/a | n/a | n/a | n/a |
| 1-40 Entrants Host Club ISCA Subtotal-Host Club |  | 25.00 2.00 1,000.00 | 20.00 5.00 800.00 | 20.00 5.00 800.00 |  |
| 41-50 Entrants Host Club ISCA Subtotal-Host Club |  | 20.00 7.00 200.00 | 15.00 10.00 150.00 | 15.00 10.00 30.00 |  |
| 51+ Entrants Host Club ISCA Subtotal-Host Club |  | 13.50 13.50 162.00 | 12.50 12.50 12.50 | 12.50 12.50 0 |  |
| Totals (exc. Late Fees) Host Club ISCA | 678.00 690.00 | 1,362.00 312.00 | 962.50 312.50 | 830.00 220.00 | 2,775 0 |

From these examples, it is apparent that the Executive Committee of the ISCA has approved a wide variety of arrangements.  Some, such as in 1977, guaranteed only 30 entrants and had an even split of the entry fees after that number.  In more recent years, the guaranteed number of boats has been 40 with the fee scale more highly weighted toward the host club within those first forty boats.  The costs incurred by the ISCA (mostly trophies) come partly out of entry fees and partly out of the annual operating budget.

The host club's portion of the entry fees of the guaranteed entrants (40 boats since 1978) are available in advance from the ISCA to pay up front expenses, down payments, or deposits which may be required.

### Other Fees and Expenses

As noted in the discussion of the budget; lunches, beverages, and the banquet should be self-sufficient.  The Finance Subcommittee Chairman may have to assist in setting the prices to insure that this goal is met.

Prior to and during the event itself, the Finance Subcommittee Chairman or some other person should be continually available to dispense any funds that are needed to cover unforeseen or sudden expenses.  Again, careful records of these should be kept.

### Financial Summary

When all the bills have been paid, a short summary should be prepared showing budgeted and actual expenses and whether the event resulted in a net profit or loss to the host fleet.  This summary, along with any description necessary to explain any unusual items or expenses, should be submitted to the ISCA Executive Committee.

In certain instances, the ISCA MAY reimburse the host fleet for a net loss in order that small or growing fleets do not hesitate to host the NCS because of the risk involved.  This is not guaranteed (explicitly or implicitly) beforehand.

## Reception

Prior to the event, this Subcommittee will have to assemble a registration packet for each entrant.  Sufficient extras should be made up to give to the Judges and Race Officers, to allow for losing some, and to allow for late entrants.  Usually 15-20 extras are sufficient.  Using the list of preregistrants supplied by the ISCA Secretary-Treasurer, each packet may be labeled and given to the person when they arrive.  Each packet must include:

| Sailing Instructions (2 copies) | Entry passes, bar tags, parking permits, etc. |
| --- | --- |
| Schedule of Events | Name tags |
| Fleet Identification Ribbons Local Map (including directions to the banquet site, if necessary) | General Information Sheet containing information on baby sitters, emergency medical and dental care, and a local phone number for Alcoholics Anonymous |
| Sail and Hull Measurement Forms | Favors or mementos (if any) |

At the registration desk (two card tables or larger), the 2-3 persons should be rotated every hour or so in order to continuously provide cheerful greeters.  This gets the hospitality off on the right foot.

If the packets are made up after the list of ISCA members is received from the ISCA Secretary-Treasurer, then the Scorecards can be already made out for the preregistered yachts, except for crew names.  The Master Record Sheets should be made out, as noted below, after the close of final registration.

The other duties of the Reception Committee are:

1.	Sell tickets for the banquet lunches, and other events.  Be certain to make the deadline for banquet tickets very plain.

2.	Point out the location of the Official Notice Board and where protest forms may be obtained.

3.	Have each participant complete the final registration form with the crew listed for each race.

4.	Receive and try to relay all messages.

5.	Point out the Measurement Forms in the packet and ask that they be returned to the Registration Desk when completed.

6.	Receive the completed Hull and Sail Measurement Forms and check for completeness.  If not complete, do not accept them.  If complete (and signed), save and set aside for the Measurement Committee.

7.	Fill out a Scorecard for each competitor. (Assuming scorecards and not computer scoring).

8.	When Registration closes, place all names and yacht numbers in order by yacht number on the Master Record Sheets.

9.	Make certain that completed Registration and Measurement Forms have been received for all registrants.  At this time, make the fleet assignments for the Championship and Challenger Fleets and post the lists along with the appropriate ribbons.

Alternately, the Measurement Forms may be turned in at either the sail measurement, yacht measurement, or weighing stations when they have been fully completed and SIGNED. This requires that one person at each of these three measurement stations collects the forms and returns them after the close of measurement to the Registration Desk.

No final registration is valid (even for a person preregistering by mail) until a signed Hull Measurement Form and Sail Measurement Form is received.  A count should be made before the Competitors Meeting that all forms have been received and any missing or incomplete forms located and completed.

Late registrations (that is, any registration other than a mailed-in registration) MUST be handled in the following manner:

1.	Proof and date of ISCA membership must be shown.

2.	If proof of membership cannot be provided, the ISCA Secretary-Treasurer may supply membership records to establish eligibility.

3.	All late fees must be paid.

The Reception Committee will need the following supplies and equipment:

Tickets.  They should be durable, of a different color for each event, and numbered.

Name Tags.  Many of these since they always get lost.  Three for the skipper plus two for each crew.

Mooring Tag.  Possibly a nametag which may be used to identify and reserve a mooring space.

Scorecards (If used).  Furnished by the ISCA.

Sailing Instructions.  Furnished by the ISCA National Race Committee or approved by the NRC and printed locally.

Schedule of Events.

Local Maps, including a map showing the banquet site.

Measurement Forms.  Furnished by the ISCA Measurement Committee or approved by the Committee and printed locally.

Mementos or favors

Pencils, felt-tipped pens, and scratch pads.

Cash box (with change).

Preassembled complimentary ticket packages for the Race Officers, Judges, and other officials.

A master ticket list showing who bought which ticket.  This will allow replacement of misplaced tickets.

All the necessary entry tags, bar tags, and parking permits.

## Housing

The Housing Committee must tackle its assignment early in order to provide shelter for the assembled racers and officials.  A variety of housing arrangements must be made including camping, cottages, and motels.  The emphasis and balance of these facilities varies with the location and theme of the event.  In 1978 at Glen Lake in northern Michigan, most housing was in cottages and camping owing to the nature of the region.  When Jolly Roger Sailing Club hosted the NCS in 1975 and 1984 in Toledo, motel rooms were more important because the regatta site was in an urban area.

One member of the Housing Committee functions as a referral service, particularly during the final weeks before the event, directing persons who have delayed their housing plans to those few places which are still available.

In each of the three types of housing (camping, cottages, and motels) a spectrum of rates should be available.  Each of these three areas presents its own difficulties, but often the local Chamber of Commerce can provide a starting list of cottages, campgrounds, and motels.

Cottages are perhaps the most difficult to arrange since they tend to be widely separated, difficult to accurately characterize based on quick inspections, and often unobtainable due to prior commitments.  Early, vigorous activity is necessary here if this is to be a major mode of housing at the event.  Prior knowledge can be used to remove locations from the list which fail to meet minimal standards of cleanliness.  As many of the remaining cottages as possible should be personally inspected and the features noted.  In particular, the number of beds, bedrooms, and other living facilities should be noted.  The availability of vacancies during the week of the NCS should be specifically requested along with the policy on reservations and check out time.

Campsites are usually fewer and much easier to reconnoiter.  Again, the availability of vacancies during the NCS, the reservation policy, and the checkout time should be noted and recorded.  Points to look for include the number and types of sites available, availability of water, electricity, and shower facilities.  Distance from the club should also be considered.  If camping is available at the club itself, it should receive top billing.

Motels should also be screened and their distance from the club, breakfast facilities, and checkout times noted.

The compiled information should be published in the Intercom in the January issue (deadline in December!) since cottages often will accept reservations beginning on January 1.

In all three types, the Committee may decide to deal in "housing futures", that is, make early reservations of blocks of campsites, cottages, and motel rooms for use by Interlakers.  This requires more effort on the part of the Housing Chairman and also continuous reevaluation of housing needs and projections since reservations which will not be needed must be canceled as early as possible to avoid financial penalties and maintain goodwill with the various facility operators.

Appropriate housing for the Judges and Race Officers should be reserved and paid for by the host club.

## Lunches and Refreshment

Lunches are an area where any club should already have some experience from other, smaller scale, regattas.  Lunches may be sold through tickets or on a cash basis.  If on a cash basis, a flat rate is usually preferable to ala' carte pricing since it eliminates a great deal of arithmetic.  In establishing prices, bear in mind the complimentary meals, which will be provided, to the Race Officers, Judges, and other officials.

Meals should be capable of being served fast and held up if there are racing delays.  The food should also hold up in hot weather and NOT BE DRY!  Adequate beverages should be on hand to quench the thirst of the sailors.

The lunch site itself should be convenient to the largest group of sailors if the mooring facilities during the noontime period are widely dispersed.

Coffee and rolls or doughnuts should be offered each morning at a reasonable fee.  The doughnut order can be adjusted each day based upon the previous day's sales.  Any surplus doughnuts can be offered at lunch rather than kept for the following day.

State or local laws as well as local facilities dictate how beer and beverage sales must be handled.  Beer and soft drinks should always be available during the registration and measurement periods.  Complimentary beverages should be provided for the Race Officers and Judges.  Charges for beer are, of course, at the discretion of the club, but this should not be a major drain on funds.  There is no requirement that beer be given away, even after the last race of the day or series.  Kegs may help keep costs down, but remember soft drinks and low-calorie beverages for the non-beer drinkers.  The need to make change can be minimized by making a flat fee for a cup and no charge for the beer to put in it.

## Social

Social and entertainment functions need not be extensive.  A minor event in conjunction with the Competitors Meeting on the evening before the first race helps to get everyone acquainted and renew old friendships.  A skit by the local fleet can help to promote the theme of the regatta.  While planning for the adults, don't forget the interests of the younger people.  The expenses for these activities should be planned for in the budget.

## Mementos

This is an optional activity.  Item may be purchased or made as a fleet or committee activity.  Various ideas include batten bags, glasses, sweatshirts, plaques, protest flags, or Styrofoam coolers.  Keep a firm eye on the costs.  In the past, this has been an area that has led to very unpleasant surprises and has made the difference between a modest net profit and a substantial loss.

## Banquet

This subcommittee makes arrangements for the ISCA Annual Banquet.  Again, costs here are very important.  Establish prices in writing with the caterer, the hall, and other suppliers.  Prices should include taxes and tip (if any).  In setting prices, consider setting separate prices for children's portions in order to maximize the turnout.

Early publicity should include a menu and a reservation form published in the issue of the Intercom that contains the Notice of Race.  The method and deadline for reservations should also be decided and published at this time along with a note about a method for obtaining refunds.  A map to the site, if not at the sailing club, should be included in the final registration packet.  The site for the banquet itself should include capacity for 3 persons per boat and include a head table for the Association officers and, if possible, the Principal Race Officer and Chairman of the Protest Committee.  Since a considerable amount of ISCA business may have to be conducted, a sound system is desirable and in some locations essential.

Again, in pricing this event, keep in mind the complimentary meals for the Race Officers and Protest Committee.

## Launching and Mooring

Planning and foresight here can go a long way toward making the registration and measuring process run smoothly.  Establish a plan well in advance so that any special equipment may be provided for in the budget or the participants may be advised what to bring in the pre-race publicity.

Although rigging and yacht measurement should be separated from he launching area itself, it may be useful to make yacht weighing an integral part of the launching process if all yachts are to be launched by a hoist.

Personnel should be available continuously to aid in the launching and trailer storage process.  Since many crews will be shorthanded at this point, this effort will avoid bottlenecks and keep the launching area clear.  Yachts should be towed or otherwise directed to their mooring spots.  A method of assigning or of claiming mooring spots is very helpful here since sailors are often quite possessive of secure or secluded mooring spaces.

Each participant should be informed or reminded at this time about any local regulations or practices concerning entering or leaving the harbor, use of ramps or parking spaces, etc.

## Clean Up

This area should not be overlooked, but simple preparation and reliable personnel are all that is needed here.  Extra trash pickups may have to be arranged to keep the yacht club's trash receptacles from overflowing during the week of the National Championship Series.  In areas were deposits are required for beer and soft drink containers, a collection method for empties will have to be established in coordination with the Lunches and Refreshment Subcommittee.  The budget for this subcommittee should include many trash bags.  Any unused bags may be resold to fleet members after the event.

## Appeal

No Judges Committee or Race Committee is infallible and each racer has the right of appeal.  The Interlake Sailing Class Association does not wish to limit the ability of the NCS entrants to correct errors in rule interpretation, but a review of decisions arising out of the event should be conducted as quickly and at as low a level as possible.

The Rules and US SAILING Prescriptions require that an appeal be heard at an appropriate local level before being submitted to US SAILING.  This function is usually carried out by the CSA (Community Sailing Association), such as ILYA or, if the club does not belong to a CSA, by one of the CSA’s in that area.

## Liability Insurance

The NCS should be covered by liability insurance to protect the host club, the host fleet, and the Association.  Since most yacht clubs already have such insurance, the easiest method of obtaining coverage is through a rider on the host club's policy to cover the activities surrounding the NCS.  It is the responsibility of the host club to obtain liability insurance for the event.

## Junior Nationals and Women’s Championship

The same principles and objectives which govern the NCS also apply to the Junior National Championship Series (JNCS) and the Women's Championship Series (WCS), but the smaller scope and different nature of these two events demand more flexibility.  The member of the NRC in charge of the Junior and Women's Championships will contact the Local Committee Chairman to establish an early measurement and weighing period for yachts sailing in the JNCS and WCS.  The Race Officers and Judges need not be the same as those used in the NCS, but they should meet similar qualifications.  Consideration should also be given to holding any protest hearings for the juniors in a public area so that they may learn about the conduct of a protest hearing without being subject to the protest itself.  The deliberations of the Judges Committee should, of course, be held privately.

## Publicity

The Local Committee is responsible for contacting local newspapers and providing news releases for local coverage.  National sailing magazines and publications should also be provided with publicity information beforehand and a report (including results) afterward.

More importantly, the Local Committee is responsible for generating and submitting the articles and information to the Intercom so that it can be published in a timely fashion.  Because this is one of the primary functions of the Intercom, it is important to get the material to the Editor ON TIME so that the publication schedules is not delayed.  The publication schedule (and even the number of issues) varies from year to year, but a suggested schedule is shown below along with copy deadlines:

| Issue | Deadline | Mailing Date | Comments |
| --- | --- | --- | --- |
| December-January | 30-Nov-85 | 15-Dec-85 | Early Housing Information |
| March-April | 28-Feb-86 | 15-Mar-86 | More Housing Information |
| May-June | 05-May-86 | 20-May-86 | Deadline after the Chiefs regatta. Contents include Notice of Race, Entry Forms, Schedule, Social Events, etc. |
| July-August | 30-Jun-86 | 15-Jul-86 | Entry Forms, etc. again. The mailing date is only about two weeks before the close of preregistration. |
| Nationals | 30-Aug-86 | 15-Sep-86 | Nationals coverage. The Publicity Chair must act quickly after the event to make this issue. |
| October-November | 31-Oct-86 | 15-Nov-86 | Fall Regatta results. |

Photos are helpful to "spruce up" a story, but typesetting fees may climb dramatically so it is best to plan an article so that several photos can be grouped together on a photo page.  The importance of good coordination and frequent communication with the Intercom Editor cannot be overestimated.

US SAILING maintains a list of national and regional sailing publications that routinely print the results of national championship regattas.  The list is usually sent to each US SAILING One-Design Class in care of the contact person, usually the class president or secretary.  If the list cannot be located, call the US SAILING Inshore Office in Portsmouth, RI on (401) 683-0800 and identify yourself as the publicity chairman for the Interlake Sailing Class Association National Championship Series.  US SAILING can easily send a duplicate list.  The list includes a report form to describe the event (dates, sailing conditions, winners and their hometowns, and scores of the top ten finishers).  Because most classes hold their nationals in July or August, it is important to finish this form quickly and mail it the week following the event.  The suggested approach is to print up mailing labels or envelopes beforehand so that the forms may be copied and mailed quickly.

# MEASUREMENT

## Introduction

As discussed in Section 3, the Local Committee is responsible for appointing a group of Measurers to staff the weighing and measuring operation, but the direction of this group comes from the ISCA Measurement Committee and the Chief Measurer.  This Section provides some guidance on discharging these duties with a minimum of effort and time.

The first step toward easing this task is to appoint a member of the host fleet as Leader of the Local Committee's Measurement Subcommittee.  This person should also be appointed by the ISCA Executive Committee to the ISCA Measurement Committee.  This arrangement neatly fulfills the requirement of direction of the measurement activity by the ISCA Measurement Committee while retaining local control over the measurers themselves.  This person should meet the following qualifications:

1.	Has assisted in measurement activities (particularly sail measurement) at a previous ISCA National Championship Series;

2.	Possesses an up-to-date ISCA Handbook with Specifications and Interpretations of the Chief Measurer; and

3.	Can provide the appropriate computer and printer to generate the ISCA Measurement Certificates at the regatta site.  The Chief Measurer may be able to provide or assist in this.

The measurement process itself can usually be split up into three separate areas: Sail Measurement, Boat Measurement, and Boat Weighing.

The ISCA has begun an innovative program to keep computerized records of boat measurement.  At registration, the measurement certificate is printed and given to the registrant.  This form then is the basis of measurement signoff (discussed below) and also is a place to record the boat's weight.  A separate form does sail measurement.

## Sail Measurement

This area is usually supervised directly by the Measurers Subcommittee Leader at least until other members of the ISCA Measurement Committee arrive at the regatta site.  The measurement area itself should be indoors (or at least covered), have a hard floor (not thickly carpeted), and about 25' x 20' or larger so that the ISCA Sail Measurement Templates can be laid out simultaneously without overlapping.  This area should be cordoned off to eliminate all unnecessary traffic but should not block access to beer and soft drink supplies, lunch facilities, rest rooms, or other essential activities.  It should also include an area where measured sails may be stacked for pickup and a labeled area where sails to be measured can be stacked IN ORDER.  Supplies that will be needed include:

Pens to fill out the Measurement Forms.  These may be ball-point or felt tipped;

Clipboards (two or more) to write on;

Weights such as bricks to anchor the measurement templates.  Tape can be used, but may mar floors and be difficult to remove from the Mylar templates too;

A stapler to shorten out-of-tolerance sails.  This is not the preferred method, but may be used as a last resort;

A 25-ft. tape measure clearly marked with the owner's name;

A desk, table, or other writing surface;

An ISCA Handbook for reference;

The ISCA sail measurement stamp and indelible ink pad (supplied by the ISCA); and

Signs to indicate where sails are to be placed and picked up.

All sailors working here should be able to direct sailors with spinnakers that are too large to the nearest coin operated laundry facilities.

Sails that have been measured in previous years and not modified in any way need not be re-measured.  These should be separated, stamped only, and moved to the pickup point as quickly as possible to relieve congestion.

Remember the "Two Minute Rule."  If you can't find the previous measurement stamp after two minutes of looking, give up and measure it again.

One worker may be designated as the keeper of the stamp and pad and should keep them at all times to avoid losing or misplacing either of these essential items.  Each person should be able to receive sails, ensure that the Measurement Form is properly filled out and signed, and segregate those sails that only need to be re-stamped.  A third person should keep the pickup point as orderly as possible, keep the sails from each owner together with each other and with the measurement form.  The remainder of the personnel can spread, measure, and fold sails.

No sail can be stamped unless it has the correct sail number and an ISCA Royalty tag.  This means that the spinnaker number must match the number on the mainsail.  Be certain to fold each sail carefully and return it to its proper bag.  As a precaution, it is best to institute a "shoes off" policy within the measurement area.

Don't hesitate to accept volunteers from the entrants themselves in order to relieve the people originally assigned to work in this area.  Many sailors have helped at other National Championship Series and are only too eager to assist, but the person in charge should witness or guide their first efforts to ensure that they are performing their tasks correctly.

## Boat Measurement

Under the ISCA's Measurement Certificate system, only boats that do not have certificates or have been modified, or have changed owners since their last measurement must be measured; other boats can have their measurement "signed off" by the owner.  The Measurement Subcommittee Leader should appoint two people to oversee this area.  This activity should take place in an area where trailers may be parked in large numbers, but not along a public street (for safety reasons).  Yachts must be measured before the masts are stepped.  An enclosed area (a van works well here) will be needed to fill out the Measurement Forms if the weather does not cooperate.  Other supplies that will be needed are:

Pens to fill out the Measurement Forms.  These may be ballpoint or soft tip;

Clipboards (two or more) to write upon;

A 25-ft. steel tape measure clearly marked with the owner's name;

A roll of half-inch electrical tape, vinyl, or plastic tape to use for spar bands;

An up to date ISCA Handbook for reference;

The bow numbers and a sheet to record which number is assigned to which boat;

The measurement templates supplied by the ISCA; and

Signs to indicate the measurement area.

Make certain that all measurement items are filled out or marked off in the Measurement Form or Certificate.  The personnel working in this area are responsible that all measurements are performed correctly.  No item should be approved until it has been measured within the specifications.  To approve an item, write the dimension measured in the designated area of the form or certificate.  Spars will have to be re-measured after new spar bands are installed in order to demonstrate compliance.

Avoid climbing on yachts with dirty feet or otherwise defacing a well-maintained yacht.  The owner may assist by holding one end of the template or tape measure to help speed up the process.  Again, don't hesitate to accept volunteers from among the sailors, but witness or guide their first efforts to ensure that they are performing their tasks correctly.

Any questions from the sailors should be referred to the members of the ISCA Measurement Committee or the Chief Measurer.

## Bow Numbers (If Used0

Bow numbers are assigned at the measurement station.  The Chief Measurer has authority on placement of numbers according to the Sailing Instructions.  The numbers should be vinyl and 8” high with “permanent” adhesive, which is less expensive, but can still be removed if done soon after the completion of the regatta.  Odd numbers should be black and even numbers white.  Numbers should be placed as far forward and high as possible.  The single digit numbers should be held in reserve for people with state registration numbers or stripe arrangements that make placement difficult.

The list of bow number assignments must be given to the scorers after the close of registration.

## Boat Weighing

The Leader of the Measurers Subcommittee should usually appoint one person to oversee this area.  This activity may take place in conjunction with the launching and may therefore need to be coordinated with the Launching and Mooring Subcommittee.  Again, an enclosed area will be needed to fill out the Measurement Forms if the weather is uncooperative.  Other supplies that will be needed are:

Pens to fill out the Measurement Forms;

Clipboards (two or more) to write upon;

An up to date ISCA Handbook for reference; and

Yacht scales (supplied by the ISCA).

The people at this station have two tasks: First, to weigh and record the weight of each boat.  Second, to verify the presence, position, and labeling of all corrector weights.

The scales will have been pre-calibrated before the event.  The electronic scale is not temperature dependent aside from some zero drift.  The weight of the bridle must be subtracted from the total weight of each boat.

The weighing personnel should also have on hand up to 100 lb. Of lead weight for resale to owners of yachts that are too light.  If so, a buyer should be located beforehand for any weight that may not be used.  In this way weight may be added to a boat which measurers in too light while it is still on the hoist to bring it up to the Association minimum weight.  The owner can then pull the boat to the side of the weighing area to permanently attach the weight as required by the Association Specifications.  Afterwards, the weighing personnel need only to certify that the weight has been attached and record the positions of the corrector weights in order to sign off on the Measurement Form.  In this way, there is no need to reweigh the boat.

One person should be designated responsible for yacht preparation.  Before a yacht is weighed, this person should personally inspect it to ensure that all required equipment (and ONLY the required equipment) is on board and that each yacht has a lifting bridle before it gets to the weighing station.  The required and prohibited equipment is listed in the ISCA Handbook under Specifications and Interpretations of the Chief Measurer, but are repeated below:

| REQUIRED | PROHIBITED |
| --- | --- |
| Hull, mast, boom, rudder, and tiller | Life jackets and preservers |
| Standing rigging (fore- and sidestays) | Paddles |
| Running rigging (all halyards and sheets) | Anchor and anchor line |
| Spinnaker pole and whisker pole (one each) | Tools, bailing bucket, and boom crutch |

Yachts that do not meet the minimum weight requirement of 650 lb. should not be launched, but set aside until they have been brought up to weight and the weight permanently attached.

## Summary

Weighing and measuring is an area that, for the majority of racers, should proceed quickly and smoothly.  Properly run, it will not interfere unduly with the registration, launching, and mooring process.

Disputes that arise and cannot be settled by reading the ISCA Handbook should be referred to the ISCA Chief Measurer.  It is emphatically not the responsibility of the Measurers Subcommittee to provide further interpretations of the ISCA Specifications.

# RACE MANAGEMENT AND JUDGING

## Introduction

No part of the National Race Committee's (NRC's) assignment is as important as approving and overseeing the Principle Race Officers of the National Championship Series (NCS).  This Section of the NRC Manual has been specifically endorsed by the ISCA Executive Committee and is a guide to insure that competent Principle Race Officers (PRO's) and Judges are retained, that they understand their authority and function, and that they are given the tools necessary to perform their function.

The NRC has the authority to conduct the regatta whereby the ISCA selects its National Champion.  The National Champion represents the class at the US SAILING Championship-of-Champions Regatta and, among other things, is a symbol to other sailors (both inside and outside of the ISCA) of the quality of competition within the Association.  Therefore, the National Championship Series must be conducted under the highest standards of race management and judging so that the best possible champion may be chosen.

On the other hand, the ISCA is basically an organization of family sailors.  The sailors participating in the NCS come from a wide variety of fleets, sailing experience, and expertise.  Although the primary purpose of the NCS is to determine a champion and an ISAF Fundamental Rule states, “A boat is solely responsible for deciding whether or not to start or to continue racing.” the Principle Race Officer must also run safe races for all competitors.  In some cases, this may mean canceling, abandoning, or postponing races for the Challengers Division if conditions warrant.

The judging of the event is also an important factor in assuring the quality of the regatta.  Poor performances by Judges seriously undermine the efforts of the NRC to present a quality event.

## Organization

The NRC has all of the rights, powers, and obligations which the Racing Rules of Sailing (RRS) delegate to the "Race Committee" except that the on the water management of the races is performed by the Race Officers and protests and Requests for Redress are heard and decided by the Protest Committee or Judges Committee.

The NRC has overall responsibility for the National Championship Series and ABSOLUTE CONTROL whenever the RC boat is docked.  The decision whether or not to attempt to start a race must be made in accordance with the sailing instructions by the NRC.  Once the Preparatory Signal for the first division has been raised, the responsibility for the conduct of the race belongs entirely to the PRO until the race is concluded and any comments, suggestions, or commands to the RO's by members of the NRC are entirely inappropriate.

The PRO is retained by the host club and approved by the NRC to conduct the races themselves.  In this, the PRO is assisted by the balance of the Race Management Subcommittee which includes the operators of the various service and stake boats as well as the race recorders, flag and signal operators, and other assistants.

The Judges observe the races on the water either from the RC boat and the stake boats or from a specific Judges Boat.  If any judge is stationed on the RC boat, the PRO should not expect the judge to perform any race management duties since, in the event of a Request for Redress, this may make the judge an interested party and therefore not able to participate in the decision.

Because the NRC has overall responsibility, it may remove any of the Race Officers or Judges at any time if it is the Committee's belief that the conduct of the person (on or off the race course) is inconsistent with the standards of the Interlake Sailing Class Association or US SAILING for Race Officers or Judges.

## Race Officers

The Race Officers (the PRO and their assistants) perform all of the duties of the race committee away from shore.  After the Preparatory Signal of the first division, any command, order, or comment by any competitor (whether or not the competitor is a member of the NRC) is not binding on the Principle Race Officer.

Any Race Officer may protest a boat under RRS 60.2 (based upon a the discussion with the NRC before the event) but the Protest Committee will handle the hearing.

The Race Officers should be competent, experienced sailors with prior experience in race management, judging, and local conditions.  Although one Judge may ride on the RC boat, the Race Officers should include sufficient personnel so that the Judge does not have to assist particularly during the crucial starting sequences.  Race Recorders should be on board specifically to record starters and finishers as well as personnel to operate radios, sound equipment, and flags.  Each of the other boats used as mark setting and stake boats should be adequately staffed and radio equipped.

## Judges

The Protest Committee or Protest Committee should be made up of experienced sailors who meet qualifications similar to those set by US SAILING for US SAILING Judges:

- be a current member of US SAILING;

- have a thorough knowledge and understanding of the current RRS, US SAILING Appeals Decisions, and ISAF Cases;

- possess judicial temperament, a reputation for mature judgment and have an outstanding reputation for integrity;

- have raced for at least three complete racing seasons in a position requiring on-the-water application of the RRS as skipper, tactician, watch captain, or navigator;

- be knowledgeable and experienced in the running of races and have performed in a major role on the water in at least three U.S. events during the last four years;

- during the last four years, have participated as a member of protest committees for at least three years and served as a chair for at least three hearings at regattas of significant importance to that region;

- be highly recommended by US SAILING members who are familiar with the protest committee or judging of the candidate and are either experienced protest committee members or US SAILING Judges; and

- Own and maintain current versions of US SAILING judging publications: ISAF Rule Book, Appeals Decisions and ISAF Cases; and Judges Manual.

The Interlake Sailing Class Association expects that the personal conduct of each Judge meet the standard prescribed for US SAILING Judges:

PERSONAL CONDUCT OF JUDGES
 The personal conduct of judges and umpires must be above reproach before, during, and after an event. Judges must comply with the Judges Standards and Practices outlined in the US SAILING Judges Manual.  They are expected to be mature and temperate, moderate in their use of alcohol, especially careful of medications, and in full control of their facilities.  A judge who has engaged in serious misconduct should be dismissed from the Protest Committee immediately

The ISCA National Championship Series is an event where the Protest Committee hears and decides protests and requests for redress and is independent of the race committee.

## Protests

All protests are handled exclusively by the Protest Committee.  The NRC or Principle Race Officer has no power to modify or overturn decisions by the Protest Committee.

In cases involving measurement protests, the Judges may take factual testimony from members of the ISCA Measurement Committee as a whole, or the Chief Measurer; but the Protest Committee must render the decision only.

Protests by the race committee under RRS 60.2 may be initiated by any Judge or Race Officer who believes that a rule infringement has occurred.  The Judge or Race Officer must fill out a protest form to provide documentation for the Protest Committee and the boat or boats named in the action, and this form must be made available to the affected boats so that they may prepare defenses.

The Protest Committee shall consider each of these actions whether initiated by a Judge or Race Officer.  Explicitly, a Judge initiating such action may be included on the Protest Committee and may participate in the decision.

## Requests for Redress

Requests for redress are a type of action which demand special procedures and extra care to insure that the regatta is managed in an absolutely fair fashion.  The responsibility for deciding Requests for Redress resides with the Protest Committee because the NRC members are usually also competitors who could be viewed as "interested parties" in the decision.  However, a Judge who is also a member of the NRC may take part in a decision on a Request for Redress.

## Selection of Race Officers and Judges

Because of their importance to the event, the PRO and Judges should be chosen well before the NCS is to take place.  In any case, all Judges, the Principle Race Officer, and the other Race Officers should meet with the National Race Committee to review the distribution responsibility, Sailing Instructions, ISCA Bylaws, and to clarify any questions that these people may have.  This meeting should occur before the Sailing Instructions are printed and before the deadline date for the issue of the Intercom which will contain the Notice of Race.  At this meeting, the PRO or the Judges may request changes in the Sailing Instructions that the NRC should consider and adopt or reject at that time.

Each Judge and Race Officer should be specifically questioned as to their background, experience, and qualifications.  This background should be used as part of the publicity surrounding the NCS to promote the event.  It should certainly appear in the same issue of the Intercom as the official Notice of Race.

If any Judges or the Principle Race Officer appears to lack the qualifications discussed above (but has already agreed to volunteer to work on this event) they should be assigned a task commensurate with their abilities such as operation of a service or stake boat.  If this occurs, the NRC and the host club must undertake an immediate search for a replacement. Last minute replacements should be strenuously avoided.

## Summary

Ideally, the major worries of the NRC should end with the Competitors Meeting prior to the first race of the National Championship.  If the RO's and Judges are well selected and prepared (and lucky), they will need no further guidance or correction to discharge their duties.  The members of the NRC will then be able to enjoy their event secure in the knowledge that the best possible National Champion will be chosen.  The Champion should be chosen by sailing skill alone, not by accidentally benefiting from poor race management or judging.  Similarly, anyone who does not become National Champion should feel that this was due solely to their not sailing as well as the Champion.

# NOTICE OF RACE

The Notice of Race must fulfill certain requirements specified by the Racing Rules of Sailing.  The forms shown below and in the other appendices contain several entries that must be filled in each year.  These are denoted by brackets "<>" which enclose a description of the entry to be supplied.

INTERLAKE SAILING CLASS ASSOCIATION

20<xx> National Championship Series

Presented by <Host Sailing Club>

<Regatta Site>

August <x-y>, 20<xx>

(Note:  Dates should span the entire event from registration to the make-up date.)

ELIGIBILITY: All persons who meet the ISCA requirements for sanctioned events contained in Article VI of the Bylaws, who are members of the Association as of <two weeks before the start of the first race>, and who have registered by <close of final registration>.

RACES:   A total of <number of races> races are planned.  A minimum of races constitutes a National Championship Series or a National Challenger Series.

SCORING: A boat’s worst score will be excluded only if <number> races (<other number> after the Qualification Series) are completed.  This changes rule A2.

TROPHIES:    Championship Perpetual: National Champion, National Championship Crew.

Championship Individual: First - tenth place skipper and crew.

Challenger Perpetual: Challenger Division Champion

Challenger Individual: First - third place skipper and crew.

Other:  Best First Nationals Outside the Top Ten, F.K. Holtzman Award (Best Fleet Participation)

REGISTRATION FEE: US SAILING Member: <entry fee>.  Non-US SAILING Member: <entry fee +$5>.  Entries postmarked after <two weeks prior to first race>: add $<late fee>.

RULES:   The Regatta is governed by the “rules” as defined by The Racing Rules of Sailing, including the ISCA Bylaws for sanctioned events. As described in Article IX of the ISCA Specifications, the Interlake is a Category C class under the ISAF Advertising Code with the additional restrictions contained in Article IX.

MEASUREMENT: Completion of the Measurement Form is a mandatory part of registration.  Measurement will be conducted only <times and dates for measurement>.

ENTRIES: Send or deliver the entry form and a check payable to the Interlake Sailing Class Association to:

Interlake Sailing Class Association

<ISCA Secretary-Treasurer>, Secretary-Treasurer

<ISCA Secretary-Treasurer's address>

ADDITIONAL EQUIPMENT:    Protest flags will be required to signal a protest.  Protest flags will be available for sale.  <any special mooring equipment needed><any equipment required by state or local law>

SCHEDULE:	<date>	<time>	Registration

<date>	<time>	Measuring

<date>	<time>	Competitors Meeting

<date>	<time>	Warning Signal, First Race

Etc.

Racing will be scheduled for <makeup date> if fewer than <# of races for throwout> have been sailed.

Other items that must appear in the same issue of the Intercom include:

Host site information, including a map, address, phone number, and whether the phone is attended or unattended.

Banquet information including menu, prices, a deadline for reservations, and a method for obtaining refunds.

Lunch information.  How are the sailors going to be fed on race days?

Housing information, including a contact person.

Memento information (T-shirts, etc.).

RACE  NOTICE

20<xx> ISCA JUNIOR AND WOMEN'S CHAMPIONSHIP

August <x-y>, 20<xx>

ELIGIBILITY: Junior: All crew, including helmsman, must be under 20 years of age on <date of first race>. Women’s: The event is open to all women.

TROPHIES:    Junior Perpetual: Junior Champion and Junior Champion Crew

Women's Perpetual: Women's Champion

Both Series: Skipper and crew, first - third place.

RACES:   Three races are planned.  There is no minimum number of races necessary to constitute a championship series.

REGISTRATION FEE:	Junior: $<Junior entry fee>

Women's: $<Women's entry fee>

Pre-registration is not required.  Registration and measurement for the Junior and Women's Championships closes at <time> on <day and date>.

RULES: The Regatta is governed by the “rules” as defined by The Racing Rules of Sailing, including the ISCA Bylaws for sanctioned events, and the sailing instructions of the ISCA National Championship Series with the following exceptions:

Article VI Section 3 of the ISCA Bylaws requiring ISCA membership does not apply.

MEASUREMENT: Completion of the Measurement Form is a mandatory part of registration.  Measurement will be conducted only <time and dates of measurement>.

ENTRIES: Send or deliver the entry form and a check payable to the Interlake Sailing Class Association to:

Interlake Sailing Class Association

<ISCA Secretary-Treasurer>, Secretary-Treasurer

<ISCA Secretary-Treasurer's address>

ADDITIONAL EQUIPMENT: See the National Championship Series elsewhere in this issue of the Intercom.

SCHEDULE:	<date>	<time>	Registration

<date>	<time>	Competitors Meeting

<date>	<time>	Warning Signal, First Race

Etc.

# ENTRY FORM

ENTRY FORM

ISCA 20<xx> National Championship Series

| NAME: | ________________________________ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| BOAT NO.: | ________________________________ |  |  |  |  |  |
| ADDRESS: | ________________________________ |  |  |  |  |  |
| CITY: | _____________________ | STATE: | _______ |  | ZIP: | ____________ |

National Championship Series

| Entry Fee – US SAILING Members:$<Entry Fee> non-US SAILING Members::$<Entry Fee> | $<Entry Fee>_________ |
| --- | --- |
| Late Fee (entries postmarked after <date>) | $<Late Fee>__________ |
| Banquet <Date and Time>: |  |
| _______ Adults @ $<Adult Fee> | $__________ |
| _______ Children @ $<Children's Fee> | $__________ |
| Banquet Subtotal: | $__________ |
| Mementos | $__________ |

Junior Nationals

| NAME: | ______________________________ |
| --- | --- |
| Junior Nationals – US SAILING Members:$<Entry Fee> non-US SAILING Members::$<Entry Fee> | $__________ |

Women's Championship

| NAME: | ______________________________ |  |
| --- | --- | --- |
| Women's Championship – US SAILING Members:$<Entry Fee> non-US SAILING Members::$<Entry Fee> |  | $__________ |
| TOTAL: | $__________ |  |

Make checks payable to "Interlake Sailing Class Association" and mail or deliver to:

<ISCA Secretary-Treasurer>

<ISCA S-T's address>

FINAL ENTRY FORM

| NAME: | ________________________________ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BOAT NO.: | ________________________________ |  |  |  |  |  |  |
| HULL COLOR: |  | ________________________ |  |  |  |  |  |
| ADDRESS: | ________________________________ |  |  |  |  |  |  |
| CITY: | _____________________ |  | STATE: | _______ |  | ZIP: | ____________ |

National Championship Series

| RACE 1 Crew:_____________________________ | Crew:______________________________________ |
| --- | --- |
| RACE 2 Crew:_____________________________ | Crew:______________________________________ |
| RACE 3 Crew:_____________________________ | Crew:______________________________________ |
| RACE 4 Crew:_____________________________ | Crew:______________________________________ |
| etc. for all races |  |

(NOTE: Substitution of any of these crews must be with the prior written consent of the National Race Committee)

Women's Championship

| NAME: | ________________________________ |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BOAT NO.: | ________________________________ |  |  |  |  |  |  |  |  |
| HULL COLOR: |  | ________________________ |  |  |  |  |  |  |  |
| ADDRESS: | ________________________________ |  |  |  |  |  |  |  |  |
| CITY: | _____________________ |  | STATE: |  | _______ |  | ZIP: | ____________ |  |
| RACE 1 Crew:_____________________________ |  |  |  | Crew:______________________________________ |  |  |  |  |  |
| RACE 2 Crew:_____________________________ |  |  |  | Crew:______________________________________ |  |  |  |  |  |
| RACE 3 Crew:_____________________________ |  |  |  | Crew:______________________________________ |  |  |  |  |  |

(NOTE: The same rules for crews apply as in the National Championship Series.  In addition, all crewmembers must be females.)

Junior Championship

| NAME: | ________________________________ |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BOAT NO.: | ________________________________ |  |  |  |  |  |  |  |  |
| HULL COLOR: |  | ________________________ |  |  |  |  |  |  |  |
| ADDRESS: | ________________________________ |  |  |  |  |  |  |  |  |
| CITY: | _____________________ |  | STATE: |  | _______ |  | ZIP: | ____________ |  |
| RACE 1 Crew:_____________________________ |  |  |  | Crew:______________________________________ |  |  |  |  |  |
| RACE 2 Crew:_____________________________ |  |  |  | Crew:______________________________________ |  |  |  |  |  |
| RACE 3 Crew:_____________________________ |  |  |  | Crew:______________________________________ |  |  |  |  |  |

(NOTE: The same rules for crews apply as in the National Championship Series.  In addition, all crewmembers must be less than twenty years old on the scheduled day of the event.)

# SAILING INSTRUCTIONS

Sailing Instructions

20<XX> ISCA NATIONAL CHAMPIONSHIP

(Dates)

1.  RULES

  - The regatta is governed by the “rules” as defined in the Racing Rules of Sailing (RRS), including the Bylaws of the Interlake Sailing Class Association.

1.2	Bow numbers will be assigned and given to each entered boat.  They shall be displayed on both sides of the hull near the bow, the actual location on each boat to be determined by the Chief Measurer.

2.  NOTICES TO COMPETITORS

Notices to competitors will be posted on the official notice board located <location of board>.

3.  CHANGES IN SAILING INSTRUCTIONS

Any change in the sailing instructions will be posted before 0900 on the day it will take effect, except that any change in the schedule of races will be posted by 2000 on the day before it will take effect.

4.  SIGNALS MADE ASHORE

  - Signals made ashore will be displayed at <location of signals>.

  - When flag AP is displayed ashore, “1 minute” is replaced by “not less than __ minutes” in race signal AP.

  - When flag Y is displayed ashore, rule 40 applies at all times while afloat.  This changes the Part 4 preamble.

5.  SCHEDULE OF RACES

  - Boats will be assigned to the Championship or Challenger Fleets based on the fleet declared on the final entry form.

  - The first races of each day are scheduled as follows.  Each Challenger Fleet race will be started following the Championship Fleet.  A total of eight races are planned for each Fleet:

| Day, Date | Fleet | ###### Harbor Signal | ###### Warning Signal |  |
| --- | --- | --- | --- | --- |
| <Day, Date> | Championship | 0900 | 1000 | Additional races may be held each day. |
| <Day, Date> | Championship | 0900 | 1000 |  |
| <Day, Date> | Championship | 0900 | 1000 |  |

  - A boat competing in the Challenger Division in instruction 5.2 above (the second start of each race) shall display from the end of her boom the Challenger Fleet pennant supplied by the organizing authority.

  - On the last day of the regatta, no warning signal will be made after <deadline day, date, and time>.

- CLASS FLAGS

Class flags will be:	Championship Fleet: 	<Description>
Challenger Fleet:  	<Description>

- RACING AREA

The racing area is <description of area>.

- THE COURSE

  - The diagrams in Attachment 1 show the courses, including the course designation number, approximate angles between legs, the order in which the marks are to passed, and the side on which each mark is to be left.

  - No later than the warning signal, the race committee signal boat will display a numeral placard designating the course to be sailed. Or
No later than the warning signal, the race committee signal boat will display the approximate compass bearing from Mark 3 to Mark 1.

  - When there is a gate, boats shall sail between the gate marks from the direction of the previous mark and round either gate mark.

- THE COURSE

  - Marks 1,2, 3, 3S, and 3P will be <mark description>.

  - New marks, as provided in instruction 11.1, will be <mark description>.

  - The starting and finishing marks will be <mark description>.

- THE START

  - Races will be started by using rule 26, with the warning signal given five minutes before the starting signal, and in the following order: Championship Fleet, Challenger Fleet.

  - The starting line will be between a <description of starting pole> on a race committee boat at the starboard end and the port end starting mark.

  - Boats whose warning signal has not been made shall avoid the starting area.

  - A boat starting later than <time interval> minutes after her starting signal will be scored Did Not Start.  This changes rule A4.1.

  - The warning signal for the Challenger Fleet in each race will be made one minute or more after the Championship Fleet start.

11. CHANGE OF POSITION OF THE NEXT MARK

  - To change the position of the next mark, the race committee will lay a new mark (or move the finishing line) and remove the original mark as soon as practicable.  The change will be signaled before the leading boat has begun the leg, although the new mark may not yet be in position.  Any mark to be rounded after rounding the new mark may be relocated without further signaling to maintain the course configuration.  When in a subsequent change a new mark is replaced, it will be replaced by an original mark.

  - Rule 33 is changed so that, instead of displaying a compass bearing, the race committee will display a green <triangle, board, or flag> if the direction is changed to starboard or a red <triangle, board, or flag> if the direction is changed to port. (Optional)

  - Except at a gate, boats shall pass between the race committee boat signaling the change of course and the nearby mark, leaving the mark to port and the race committee boat to starboard.  This changes rule 28.

12. THE FINISH

  - The finishing line will be between a staff displaying a <color of flag> flag on a race committee boat and the port end finishing mark.

  - When the course is shortened at a gate, a race committee boat near the gate will display flag “S” and boats shall finish by sailing through the gate from the direction of the previous mark.  The finishing line will be between the gate marks.  This changes race signal “S”.

13. TIME LIMITS

  - The time limit is <time limit>.

  - Boats failing to finish within 30 minutes after the first boat finishes will be scored "Did Not Finish."  This changes rule 35 and A4.1.

14. PROTESTS AND REQUESTS FOR REDRESS

  - When a boat intends to protest an incident in the racing area that she is involved in or sees, she shall conspicuously display a red flag at the first reasonable opportunity and continue to display it until she is no longer racing. (This changes racing rule 61.1(a).)

  - Protest forms are available at the race office.  Protests shall be delivered there within the protest time limit

  - The protest time limit is 60 minutes after the race committee boat docks after the last race of the day. The same protest time limit applies to all protest by the race committee and Protest Committee and to requests for redress.  This changes rules 61.3 and 62.2.

  - Protest notices will be posted within 15 minutes of the protest time limit to inform competitors of hearings in which they are parties or named as witnesses.  Hearings will be held at <location of protest room> beginning at the close of the protest time limit.

  - Notices of protest by the race committee or Protest Committee will be posted to inform boats under rule 61.1(b).

  - For the purpose of rule 64.3(b) the “authority responsible” is the Chief Measurer of the Interlake Sailing Class Association.

  - Breaches of instructions 10.3, 16, 17.2, 18, 19, and 20 will not be grounds for a protest by a boat.  This changes rule 60.1(a).  Penalties for these breaches may be less than disqualification if the protest committee so decides.

  - On the last day of the regatta, a request to reopen a hearing shall be delivered
(a) within the protest time limit if the party requesting reopening was informed of the decision on the previous day; or
(b) no later than 30 minutes after the party requesting reopening was informed of the decision on that day.
This changes rule 66.

15. SCORING

  - The Low Point scoring system of Appendix A shall apply.

  - Five races for each of the Championship and Challenger Fleets are required to constitute a series.

  - The following is substituted for rule A4.2:  "A boat that does not finish or retires after finishing will be scored points for the finishing position one more than the last place finisher.”  A boat penalized under rule 30.2, or 44.3 shall be scored points as provided in rule 44.3(c)."

16. SAFETY REGULATIONS

A boat that retires from a race shall notify the race committee as soon as possible.

17. REPLACEMENT OF CREW OR EQUIPMENT

  - Substitution of competitors beyond the final entry list will not be allowed without prior written approval of the race committee.

  - Substitution of damaged or lost equipment will not be allowed unless approved by the race committee.  Request for substitution shall be made to the committee at the first reasonable opportunity.

18. EQUIPMENT AND MEASUREMENT CHECKS

A boat or equipment may be inspected at any time for compliance with the class rules and sailing instructions.  On the water, a boat can be instructed by a race committee measurer to proceed immediately to a designated area for inspection.

19. SUPPORT BOATS

Team leaders, coaches and other support personnel shall stay outside areas where boats are racing from the time of the preparatory signal for the first Fleet to start until all boats have finished or the race committee signals a postponement, general recall, or abandonment.

20. RADIO COMMUNICATION

A boat shall neither make radio transmissions while racing nor receive radio communications not available to all boats.  This restriction applies to mobile telephones.

19. DISCLAIMER OF LIABILITY

Competitors participate in the regatta entirely at their own risk.  See rule 4, Decision to Race. The organizing authority will not accept any liability for material damage or personal injury or death sustained in conjunction with or prior to, during, or after the regatta.

Attachment 1  Courses

| Course 1 - Gold Cup | Course 2 - Olympic |
| --- | --- |
| Start-1-2-3-1-Finish Marks to Port | Start-1-2-3-1-3-Finish Marks to Port |
| Course 3 - Double Olympic | Course 4 - America's Cup |
| Start-1-2-3-1-3-1-2-3-Finish Marks to Port | Start-1-3-1-3-1-3-Finish Marks to Port |

# NRC QUESTIONAIRE

NAME:________________________________________________________

Before completing this checklist, read through the NRC Manual.  The NRC must supply certain items to the host club, perform certain tasks during the week of the Nationals, and oversee all aspects of the event.  The Association expects each member to select one item from each of the three categories below.  If you have no preference, leave the category blank and the NRC Chairman will make the assignment.  In addition, some reassignments may be necessary if volunteers don’t cover all the bases.

I.  Items To Be Supplied By the NRC

| _____ Notice of Race | ______ Sailing Instructions |
| --- | --- |
| _____ Trophies | ______ Challenger Fleet ribbons |
| _____ Registration forms and General Information Sheets |  |

II. Tasks During the Event

| _____ Scoring | _____ Liaison with Junior and Women's Championships |
| --- | --- |
| _____ Registration - This will involve taking the final registration forms and transferring the information to the Scorecards and scoring forms. |  |

III.  Local Committee Assistance and Coordination

In this category, each person is not expected to take part in these activities, but to provide any guidance that the Local Committee may require and to insure that the Local Committee's responsibility is fulfilled.

| _____ Reception | ______ Launching and Mooring |
| --- | --- |
| _____ Lunches and Refreshment | ______ Cleanup |
| _____ Social | ______ Appeal |
| _____ Mementos | ______ Finance |
| _____ Banquet | ______ Publicity |

Return To:	<NRC Chairman>

<NRC Chairman's Address>

Deadline:	<2 Weeks before first meeting of NRC>

# REVISION LOG

| DATE | ACTION |
| --- | --- |
| 04-Nov-80 | First draft of Section VIII Race Management and Judging completed. Copy given to F.K. Holtzman for transmission to D. Rengel via ISCA Executive Committee meeting. |
| 02-Dec-80 | First draft of NRC Manual (exc. Appendix III) completed. |
| 05-Dec-80 | Spellings and typographical errors corrected. |
| 17-Dec-80 | Comments from T.F. Ehman Sr. received. |
| 18-Dec-80 | Draft revised. Judges Committee given authority to hear Requests for Redress. Organization chart revised to indicate NRC approval of selection of Judges and to add the ISCA Measurement Committee. |
| 19-Dec-80 | Spelling and typographical errors corrected. Copy printed for distribution to ISCA Executive Committee. |
| 08-Jan-82 | Added Section V.M Publicity to Local Committee. Copy printed for distribution to 1982 NRC. 21-Dec-82 Updated Sailing Instructions (Appendix III) to include 1982 features used at Sandusky. Added trophy list. Expanded guidelines on banquet site. Added Junior National Notice of Race. Copy printed for distribution to 1983 NRC with extras to ISCA Secretary-Treasurer for answering inquiries. |
| 19-Dec-83 | Updated text to remove "Historical Precedent" as unnecessary under current policies and sailing instructions. Added trophy list to Notice of Race. |
| 27-Nov-84 | Updated text for 1985. Added Appendix IV (Questionnaire), Women's Championship Notice of Race and Entry Form, and better definition of RM authority. Revised item about lead on hand during boat weighing. Copy printed for 1985 NRC. |
| 03-Dec-84 | Sample timetable added to Section I. |
| 01-Dec-85 | Added Intercom schedule under Section V.M Publicity. Repaginated and printed copy for 1986 NRC. |
| 12-Oct-86 | Revised Sailing Instructions (Appendix III) with the following changes: 1. Included reference to Rule 5.4(c)(iv) to allow the RM to abandon the race based upon a change in weather conditions (i.e. major wind shifts). 2. Added words to indicate that compass courses will not display the last zero. 3. Finish mark will now be described and all references to the last weather mark are removed. 3. Rule 51.1(c) now applies without code flag "I". 4. All scoring is moved to Section IX and an explicit chart shows discarded races and when throwouts are used. 12-Oct-86 5. Section V (Course) is modified to include the windward-leeward-windward legs and the diagram is changed to make the possibility of starboard mark roundings explicit. 6. Ribbons are described under Section III (Racing Procedure) for Elimination and Challenger Division races with the added requirement that they be visible to the Race Manager and the definition that they are not "part of the boat." 7. Spelling and clerical corrections. 8. The Sample Timetable (Preface) was modified to indicate that the Executive Committee meeting usually falls on the Sunday before the Superbowl. A copy of Appendix III was printed for adoption by the ISCA Executive Committee at its Fall meeting. |
| 01-Apr-89 | Appendix III (Sailing Instructions) was updated to conform to the 1989-92 IYRU Rules. |

| DATE | ACTION |
| --- | --- |
| 24-Aug-89 | Appendix III (Sailing Instructions) was updated to incorporate the changes developed for the 1989 Nationals, primarily the 720 Rule wording revised to follow IYRU Appendix 3. |
| 14-Apr-90 | Appendix I (Race Notice) was updated to remove the requirement that a Junior or Women's Nationals helmsman be a member or the spouse or ward of a member of the ISCA. This change was first used in 1989 to boost participation in these events. The Junior Nationals age limit was raised to 20 for the same reason. |
| 13-May-90 | Chapter 2 (Organization) was redrawn to incorporate the organization chart directly into the text. The only change was to make the chart reflect the text that the NRC approves the selection of the Race Manager as well as the Judges. |
| 07-Oct-90 | Changes made for 1991. 1. Local Committee Section V.B. Reception changed to note the requirement to gather forms from all entrants and that the A,B,C, and D Group assignments should be made after the close of final registration. 2. Appendix I Race Notice was modified to include the address and phone number of the host club. 3. Appendix I Race Notice was also modified to state that the makeup day would be used if there were not enough races for a throwout. 4. Appendix III Sailing Instructions were modified to list the starting times for the Elimination Series. |
| 17-Aug-91 | Appendix III Sailing Instructions were modified to state that IYRU Rule 4.4 (a)(i) System 1 (not "(ii)") is the starting system. Also, the scoring table was modified so the Elimination Series scores are only discarded if six or more races are held. |
| 20-Feb-92 | V.L Publicity was expanded to describe the US SAILING Regatta Reporting Service. "USYRU" changed to "US SAILING" in all chapters and appendices. |
| 15-Jun-92 | Appendix III (Sailing Instructions) revised: 1. Numerous spelling errors corrected. 2. Helmsman added to I. Rules to reflect a proposed Bylaw change. 3. IV. Schedule was changed to add a specific time limit for use of the make-up day was added. The makeup day is not used if enough races have been conducted to use a throwout. 4. Rule 8 reference was added to VIII. Recalls. 5. XI. Scoring was modified to clarify how the Elimination Series scores are discarded. |
| 05-Dec-94 | Appendix III Sailing Instructions was re-written to follow the US SAILING Sailing Instruction Guide (Appendix C2 of the 1993-96 IYRR). |
| 06-Dec-94 | The sample timetable was updated to indicate the new deadline for submission of NCS bids approved by the Executive Committee 15-Oct-94. |
| 14-Dec-94 | Section II Organization was updated to show the ISCA as the "Organizing Authority" as discussed in the rules, changed "judges" to "Protest Committee" and "Race Manager" to "Principle Race Officer" which is the current US SAILING usage. Section III Distribution of Responsibility was revised to indicate the use of Lotus 1-2-3 spreadsheets for scoring, as has been done for the last four years, remove "Best Family Team" and "Most Improved" trophies, and change to "Race Officer" and "Protest Committee." Fleet ribbons (all one color) replace the Challenger and A,B,C,D ribbons. |

| DATE | ACTION |
| --- | --- |
| 9-Feb-95 | The Manual was revised in several areas: 1. All Sections were translated from MultiMate to Word for Windows 2.0. 2. Section I Introduction was revised to include all material previously in Sections I, II (Organization), and III (Division of Responsibility). 3. Section IV. National Race Committee was renumbered as Section II and the scoring duties were rewritten to encompass the use of the Lotus spreadsheet instead of scorecards. 4. Section V. Local Committee was renumbered as Section III and revised to include the material previously in Section VI. Finances. 5. Section VII. Measurers was renumbered as Section IV. Measurement. The material was revised to include the new ISCA Measurement certificate and to reflect current Measurement Committee practice. 6. Section VIII. Race Management and Judging was renumbered as Section V |
| 5-Apr-95 | Appendix I was revised to remove the Best Family Team and Most Improved awards which have not been awarded in the last several years. The Junior Champion, Junior Champion Crew, and Women's Champion perpetual crews were added to the Race Notice. |
| 8-Aug-95 | Section I Introduction was revised to list the preference for alternating between inland and Great Lakes sites, the "traditional" dates, and the requirement to submit the bid by mid-October of the second year previously. |
| 16-Nov-97 | Appendix III was rewritten to conform to the 1997-2000 Racing Rules of Sailing and to eliminate references to the Elimination Series, based on the experience in 1997. |
| 10-Jan-99 | Several minor revisions: - All sections saved in Word For Windows 6.0/Windows 3.1 - Minor editorial changes (spelling, etc.) in all sections and appendices. Revision dates were not changed since the differences reflect no substantive or policy changes. - A table of number of entrants and “visitors” was added to aid in estimating participation and therefore entry fees in Section III. - Section V Race Management And Judging was revised to change “Race Manager” to “Principle Race Officer,” update the qualifications and standards of conduct for judges, and conform to the 1997-2000 Racing Rules of Sailing |
| 9-Jan-00 | Document redone in Word 97. Section numbering changed to “1.1.1”, etc. Table of contents added. Several grammatical corrections based on Bill Gates’ grammar preferences. |
| 19-Feb-00 | Minor corrections to cross-references. “Skippers Meeting” and “Race Notice” changed to “Competitors Meeting” and “Notice of Race” throughout. |
| 13-Jan-01 | Wording added to Sailing Instructions to deal with new ISAF Eligibility Code. |
| 28-Dec-01 | Revised Notice of Race to show 21st century dates (e.g. “20<xx>”) Revised Sailing Instructions to make signaling a new course either by compass or by red/green, depending on the venue. Revised Sailing Instructions to make the Challenger warning signal at least one minute after the Championship start. Revised Sailing Instructions to conform to 2001-4 US SAILING Sailing Instruction Guide and Racing Rules of Sailing. |
| 10-Mar-02 | Revised Sailing Instructions to closer conform to the 2001-4 US SAILING Sailing Instruction Guide. |
| 18-Aug-02 | Revised Sailing Instruction 14.7 to correct an error in numbering. |
| 25-Aug-02 | Added Entry Fee to table and updated Nationals Participation chart through 2002 |
| 19-Nov-02 | Corrected US SAILING location to Portsmouth, RI and minor update to 3.2.1 Entry Fee. |

| DATE | ACTION |
| --- | --- |
| 23-Nov-02 | Protest flag requirement in the Sailing Instructions reworded to conform to RRS. Minor grammatical and spelling updates. (N.B.: 14,211 words, Fleisch-Kincaid=10.9) |
| 18-Jan-03 | Changes approved by ISCA Executive Committee |
| 19-Jan-03 | Revisions to Section 1.1 regarding dates of ILYA Junior Bay Week and Bay Week as well as school starting constraints. Sample calendar inserted. |
| 22-Feb-03 | Revisions to Section 6 Notice of Race and Section 7 Entry Form: “Host Sailing Club” replaces “ISCA Fleet Number” because the club carries the liability insurance. “RULES” changed to conform to RRS J2. “ENTRY FEE” changed to show a differential entry fee as the default, since this is a condition for any club that is either an US SAILING Golden Anchor Club or a club using the US SAILING Regatta Liability Insurance. Applies to NCS, Women, and Juniors. “ADDITIONAL EQUIPMENT” now includes a protest flag as the default. “APPEALS” added to state that there is no appeal in the Qualification Series. “ENTRIES” changed to insert “or deliver” after “send”. |
| 15-Jul-05 | Revised Section 1.3 to reflect the elimination of the 14-day membership requirement and that the local committee should print the Hull Measurement and Sail Measurement Forms supplied by the Measurement Committee. Scoring software in Section 2 and elsewhere revised to “Excel spreadsheet or other software” in several locations to reflect the availability of various programs and unavailability of Lotus 1-2-3. Section 3.2.1 Entry Fee revised to include data from 2003-4 and the 2001 Entry Fee. Various minor revisions. |